## Sheet1
Category | Work Item | Status | Cost
Main menu | Graphics | Incomplete | 2-4 hours
Main menu | Buttons - Play, How to Play, Quit | Complete | 1 hour
Main menu | Buttons - style colors | Complete | 2 hours
Main menu | Buttons - style shadowing | Complete | 1 hour
Main menu | Buttons - style highlighting effects | Complete | 2 hours
Main menu | Buttons - style click effect | Complete | 1 hour
Main menu | Adding How to Play image/ main menu bg | Complete | 1 hour
Game screen | Creating a player sprite | Incomplete | 1 hour
Game screen | Coding a player controller | Incomplete | 4 hours
Game screen | Creating enemy sprites | Incomplete | 1-3 hours
Game screen | Coding enemy ai | Incomplete | 3-5 hours
Game screen | Coding player projectiles | Incomplete | 2 hours
Game screen | Coding enemy projectiles | Incomplete | 2 hours
Game screen | Implementing a score system | Incomplete | 1 hour
Game screen | Implementing lives | Incomplete | 2-4 hours
Game screen | Adding menu button | Incomplete | 1 hour
Game screen | Creating bg graphics | Incomplete | 2-4 hours
Game screen | Adding levels | Incomplete | 3-5 hours
Game screen | Pausing the game while the menu button is active | Incomplete | 2-4 hours
Game screen | Creating a boss ai | Incomplete | 2-4 hours
Game screen | Creating boss graphics | Incomplete | 2-3 hours
Game screen | Creating a victory screen | Incomplete | 2 hours
Game screen | Creating victory graphics | Incomplete | 2 hours
Game screen | Small graphics for ships exploding, etc | Incomplete | 3-5 hours
Game screen | Linking sound effects to actions | Incomplete | 2 hours